**PLANNING MEETING NOTES**

***------------Sprint 3------------***

***14/11/2021 - 28/11/2021***

**1. General:**

Date: 14/11/2021 (Sunday)

Start: 9h00

End: 9h30

Duration: 30 mins

Content:

* Description of PA3 for members to understand.
* Clarifying what is difficult,simple of the project to minimize problems arising from members while working.
* Divided into many smaller tasks , suitable for one person.
* Week 01, continue to develop the front end.
* Week 02, start working with the database.
* After assigning tasks, solve each member's questions (if any), then end the meeting

**2.Details:**

**1.Present:**

1/ Bui Huynh Trung Nam

2/ Hoang Huu Giap

3/ Ngo Truong Tuyen

4/ Nguyen Phan Vu

5/ Nguyen Tan Viet

**2.Absent:**

Empty

**3.Tasks and assignments:**

*\*\*Priority tasks are marked in yellow*

**Week 01:**

| **STT** | **Description** | **Start Date** | **End Date** | **Responsibility** |
| --- | --- | --- | --- | --- |
| **1** | **Make plan for sprint 3** | Sunday, 11/14/2021 | Sunday, 11/14/2021 | Bui Huynh Trung Nam |
| **2** | **Update Trello** | Sunday, 11/14/2021 | Sunday, 11/14/2021 | Nguyen Tan Viet |
| **3** | **Write 1st weekly meeting report** | Wednesday, 11/17/2021 | Wednesday, 11/17/2021 | Nguyen Phan Vu |
| **4** | **Write planning meeting notes** | Sunday, 11/14/2021 | Sunday, 11/14/2021 | Nguyen Phan Vu |
| **5** | **Write 1st weekly report** | Thursday, 11/18/2021 | Thursday, 11/18/2021 | Bui Huynh Trung Nam  Ngo Truong Tuyen |
| **6** | **Update use-case specifications** | Sunday, 11/14/2021 | Wednesday, 11/17/2021 | All members |
| **7** | **Update project plan section 4** | Sunday, 11/14/2021 | Wednesday, 11/17/2021 | Hoang Huu Giap  Nguyen Tan Viet |
| **8** | **Gather and connect (source code)** | Sunday, 11/14/2021 | Sunday, 11/21/2021 | Nguyen Tan Viet |
| **9** | **Synchronize (front-end)** | Sunday, 11/14/2021 | Sunday, 11/21/2021 | Nguyen Tan Viet |
| **10** | **Define software architecture** | Monday, 11/15/2021 | Tuesday, 11/16/2021 | Hoang Huu Giap  Nguyen Phan Vu |
| **11** | **Class diagram** | Thursday,, 11/18/2021 | Saturday, 11/21/2021 | Bui Huynh Trung Nam  Ngo Truong Tuyen |
| **12** | **Login-out, change password form (front-end)** | Monday, 11/22/2021 | Monday, 11/22/2021 | Hoang Huu Giap |
| **13** | **Landing page (front-end)** | Tuesday, 11/23/2021 | Tuesday, 11/23/2021 | Bui Huynh Trung Nam  Ngo Truong Tuyen |
| **14** | **Use-case specification: Movie view page (trailer, comment, rating, add to favor)** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Bui Huynh Trung Nam |
| **15** | **Use-case specification: View and edit profile** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Bui Huynh Trung Nam |
| **16** | **Use-case specification: Upload (review, trailer,.)** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Hoang Huu Giap |
| **17** | **Use-case specification: Edit (review,..)** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Hoang Huu Giap |
| **18** | **Use-case specification: Favorite list** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Hoang Huu Giap |
| **19** | **Use-case specification: History** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Ngo Truong Tuyen  Nguyen Phan Vu |
| **20** | **Use-case specification: Report** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Ngo Truong Tuyen |
| **21** | **Use-case specification: Classify movie** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Nguyen Phan Vu |
| **22** | **Use-case specification: Register account** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Nguyen Tan Viet |
| **23** | **Use-case specification: Login(out)** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Nguyen Tan Viet |
| **24** | **Use-case specification: Movie Ranking View** | Sunday, 11/14/2021 | Tuesday, 11/23/2021 | Nguyen Tan Viet |
| **25** | **Read document - self learning** | Sunday, 11/14/2021 | Sunday, 11/28/2021 | All members |

**Week 02:**

| **STT** | **Description** | **Start Date** | **End Date** | **Responsibility** |
| --- | --- | --- | --- | --- |
| **1** | **Design database** | Wednesday, 11/17/2021 | Saturday, 11/24/2021 | Bui Huynh Trung Nam  Ngo Truong Tuyen |
| **2** | **Create database** | Wednesday, 11/24/2021 | Saturday, 11/27/2021 | Nguyen Tan Viet |
| **3** | **Write 2nd weekly meeting report** | Wednesday, 11/24/2021 | Wednesday, 11/24/2021 | Nguyen Phan Vu |
| **4** | **Update Trello** | Wednesday, 11/24/2021 | Wednesday, 11/24/2021 | Nguyen Tan Viet |
| **5** | **Write review meeting notes** | Friday, 11/26/2021 | Friday, 11/26/2021 | Nguyen Phan Vu |
| **6** | **Write 2nd weekly report** | Thursday, 11/25/2021 | Thursday, 11/25/2021 | Hoang Huu Giap  Nguyen Tan Viet |
| **7** | **Content collections** | Thursday, 11/25/2021 | Thursday, 11/25/2021 | All members |
| **8** | **Connect Database** | Wednesday, 11/24/2021 | Saturday, 11/27/2021 | Hoang Huu Giap  Nguyen Phan Vu |
| **9** | **Menu and button (front-end)** | Wednesday, 11/24/2021 | Saturday, 11/27/2021 | Nguyen Tan Viet |
| **10** | **Create child-pages (front-end)** | Wednesday, 11/24/2021 | Saturday, 11/27/2021 | Nguyen Tan Viet  Nguyen Phan Vu |
| **11** | **Unit test and release** | Friday, 11/26/2021 | Sunday, 11/28/2021 | Hoang Huu Giap  Nguyen Phan Vu |

***--KẾT THÚC--***